## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-07-h lowercase h
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | ✓ | BH;03/18/2024
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | ✓ | BH;03/18/2024
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | ✓ | BH;03/18/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | ✓ | BH;03/18/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | ✓ | BH;03/18/2024
As as a USER I want to SIGN/LOG IN so that I CAN ACCESS THE SITE. | Given I ENTERED THE CORRECT USERNAME AND PASSWORD AND RIDDLE when I LOG INTO THE SITE then I SHOULD HAVE ACCESS TO THE SITE. | ✓ | YC;03/18/2024
| Given that I am on the u-fund site when I am not logged in then I must see a means to login and sign up | ✓ | YC;03/18/2024
| Given I HAVE ENTERED A VALID USERNAME AND PASSWORD when I SIGN UP then I HAVE AN ACCOUNT AND CAN LOG INTO THE SITE. | ✓ | YC;03/18/2024
| Given I CORRECTLY ENTER THE ADMIN USERNAME when I LOG IN then I SHOULD HAVE ACCESS TO THE MANAGER. | ✓ | YC;03/18/2024
As a Manager I want to manage my needs so that helpers will fund them. | Given I am logged in as admin when I am on the cupboard page then I expect to see a means to add a new need.
Given I am logged in as admin when I add a new need then I expect to see that need in the cupboard.
Given I am logged in as admin when I click on a delete need button then I expect the need to be removed from the cupboard.
Given I am on a need's detail page when I edit the need then the system should update the need for the future.
Given I am logged in when I am on the homepage then I expect to see a means to search.
Given I am logged in when I type into the search bar then I expect to see results for individual needs.